## Q&R
Propective Bidder Q&A
Project : 5MW Solar farm with 2.5MW BESS near Kokopo in East New Britain, PNG
Date : 2021.11.29
No | Description |  | Question | Response
| item | contents
1 | Project overview | This project has received approval from the PPL Board and Kumul Consolidated Holdings(KCH). | What company is KCH? (Role in this project) | KCH represents the Government as shareholder of PPL
2 |  | be suitably qualified and experienced in financing, ~ and operation solar farm. | Please, provide specific qualifications guideline. Are the total qualifications of the consortium companies ? | The bidding company must demonstrate and provide proof that it has experience and the capacity/capability to finance, design, procure, construct and operate the solar farm with its consortium or partners.
3 |  | "small scale generation project" which reserves generation licenses to Papua New Guinea Citizen Companies | Is participation of PNG company essential? ▶ Is it possible to participate in the bidding in the form of a JV or SPC with a local company (PNG Citizen Companies)? If possible, is there a distinction in the composition of shares? | PNG Citizen Companies is not defined in the National Energy Authority Act, however PPL has sought guidance from the regulator, the National Energy Authority, who has responded in writing that “PNG Citizen Company” should be interpreted in line with the Investment Promotion Act view of such terminology and as such should refer to a PNG registered company with at least 51% shareholding owned by PNG citizens. Please be aware that formal amendment to the relevant legislation to reflect this definition still needs to occur. In view of the above explaination, international companies are at liberty to form SPC or JV with local companies as long as at least 51% of the shareholding of the SPV or JV company is owned by PNG citizens
4 | Generating Facility | 9,000MWh(minimum) First-year energy production. | What is the rationale for minimum 9,000MWh? Refer to Global Solar Atlas by Worldbank group, if there are installed 5MW GF, total PV power output is 7,202MWh per year. To match the minimum 9,000MWh, there should be installed 6.5MW GF. attached GSA report at next tab. Please, provide sunshine and weather data of the site. | The feasibility study was conducted on a 5MW AC rated solar farm with approximately 6.5MW of solar panels (DC) capacity installed. 9,000MWh is the requirement and the solar farm should be designed by the IPP to produce this amount of energy
5 | Site Details | the land | What is the current conditions of the site? Is it flat? Or curvatures? Please, provide a topographic map showing the altitude. Where is the nearest port? And provide conditions of road from the port to the site. | Refer to the attached topographical drawing of the intended land. This should be taken as a guide only, as it describes a parcel of 40Ha, of which only 10Ha will be available (which still to be determined). The land parcel itself may also change.
6 | SCADA & Communications | the Seller is to allow for a SCADA & Communications system to be implemented which will provide PPL with the ability to monitor and react to system dynamics and alarms. | Where will you intall the system? And what is the distance? Who is responsible for work outside site boudaries? | Please refer to the response to the previous question and information provided in the EOI document. PPL will be responsible for work outside the site boundaries.
7 | Tax exemptions | PPL may seek tax exemptions for the project from the Government of PNG. | Are there any chances of getting tax benefits in the future? Kindly provide information on the legal tax rates applicable to solar PV generation company or licensed company according to this project implementation. | PPL cannot predict whether or not tax exemptions will be granted to renewable energy projects in the future. Currently, the Import Duties and Stamps, GST and Corporate Tax are still applicable
8 | Schedule | financial close: 16 December 2022 | There are Just 4 months for securing finance. It is quite lack of physical time of preparing finance | Your feedback is noted. Please provide your expected timeline in the EOI response.
|  | EPC: Jan. 2023~ Nov. 2023 | EPC period is also not enough time for preparing main equipment, panels, ESS. | Your feedback is noted. Please provide your expected timeline in the EOI response.
|  |  | Could it extend that period? | At this stage PPL does not wish to extend the timeline, and asks EOI respondents to work within the timeframe provided as much as possible and provide their own timelines for the work required.
9 | PPA Termsheet | Delay to COD | Provide detail delay damages. | It will be based on the cost of providing alternative generation to cover up for the shortfall in genration, especially diesel and associated costs, in the event of delayed COD by the IPP
10 |  | PPL securities | Who will guarantee the payment? | The Government of PNG will not provide a sovereign guarantee for the project , however other partial guarantee mechanisms may be available through multilateral partners and will be explored during the full tender phase of the project
11 |  | Currency | Can it change currency Kina to USD? | No
12 |  | underperformance fees | What is a limit on payment for underperformance fees? 5%, 10% of minimum output, etc | Liquidated Damages in such circumstances will be discussed in detail later but simply it will the cost of PPL providing the back up generation to meet the shortfall which should have been provided for by the IPP and most is the diesel generation cost. This is the same as Delay in COD
13 |  | Insurance | Provide minimum insurance coverage | We are looking for Respondents to provide their comments to the EOI termsheet in their EOI response
14 |  | Termination | Provision of compensation or penalty for premature termination | We are looking for Respondents to provide their comments to the EOI termsheet in their EOI response
15 | others | Equipment | Are there no country-of-origin restrictions for equipment? Are there any advanages to using equipment from a specific country? | At this stage PPL does not have a comment on this. We are looking for Respondents to explain the benefits of their offer in their EOI response